## 10M50083M
coach_number | phase | section | task | hours | completed | completed_date
10M50083M | Completion | Structural | 3.1 Cut and replace old end step
10M50083M | Completion | Structural | 3.2 Straighten interior floor channels
10M50083M | Completion | Structural | 3.3 Remove all screws on the floor channels
10M50083M | Completion | Structural | 3.4 Drill water ingress holes on body end
10M50083M | Completion | Structural | 3.5 Fix damaged existing bracket on the underframe
10M50083M | Completion | Structural | 3.6 Remove rust on the body using chipping hammer if rust detected is too deep, cut it and replace with new component
10M50083M | Completion | Structural | 3.7 Inspect and weld all monsoons holes roof
10M50083M | Completion | Structural | 3.8 Weld gutter holes
10M50083M | Completion | Structural | 3.9 Weld and grind rust affected areas on the sole bar
10M50083M | Completion | Structural | 3.10 Weld or replace all damaged small components
10M50083M | Completion | Structural | 3.11 Modify seat frames
10M50083M | Completion | Paint Works | 4.1 Shot blast coach sole bar
10M50083M | Completion | Paint Works | 4.2 Clean the shot blast surface with air
10M50083M | Completion | Paint Works | 4.3 Shot blast BUP small components
10M50083M | Completion | Paint Works | 4.4 Shot blast Coachbuild small components
10M50083M | Completion | Paint Works | 5.1 Clean dirt/dust inside the coach
10M50083M | Completion | Paint Works | 5.2 Auto coat interior
10M50083M | Completion | Paint Works | 5.3 Wash the underframe
10M50083M | Completion | Paint Works | 5.4 Auto coat under frame
10M50083M | Completion | Coach Build | 6.1 First water test - Check the coach is fully sealed.
10M50083M | Completion | Coach Build | 6.2 Spray pressurized water where sealant is applied (on the panel joints)
10M50083M | Completion | Coach Build | 6.3 Check if there is any leaks on windows
10M50083M | Completion | Coach Build | 6.4 Check if there is any leaks on monsoons
10M50083M | Completion | Paint Works | 7.1 1st Prime preparation - Sanding, Bodyfiller, Sanding , & Apply 1st primer coat
10M50083M | Completion | Paint Works | 7.2 2nd Prime preparation - Sanding, Sealing (Sika Flex) & Apply final coat (different colors)
10M50083M | Completion | Electrical | 8.1 Inspect all electrical wiring
10M50083M | Completion | Electrical | 8.2 Route train line through the conduits and ensure continuity - Body Ends, Doors, Control box, Lights, PA switch, Emergency push button, QSA
10M50083M | Completion | Electrical | 8.3 Terminate cables, lug, insert I-dentS, prepare & connect bogie earth straps
10M50083M | Completion | BUP | 9.1 Mechanical Draw gear/coupler installation - Fit draw gears on both ends
10M50083M | Completion | BUP | 9.2 Fit draw-gear top guides
10M50083M | Completion | BUP | 9.3 Fit carrier plate/draw-gear cover plate
10M50083M | Completion | BUP | 9.4 Fit side plunger springs
10M50083M | Completion | BUP | 9.5 Fit wear plate in a side plunger
10M50083M | Completion | BUP | 9.6 Assemble & fit side plunger springs & spring guide
10M50083M | Completion | BUP | 9.7 Fit coupler web plate and fit coupler guides
10M50083M | Completion | BUP | 9.8 Fit coupler casting & secure them with right sized bolts and split pins
10M50083M | Completion | BUP | 9.9 Fit coupler & secure coupler with split pins
10M50083M | Completion | BUP | 9.10 Fit casting and secure
10M50083M | Completion | BUP | 9.11 Fit buffer rod & split pins
10M50083M | Completion | BUP | 9.12 Fit buffer beams plate
10M50083M | Completion | BUP | 10.1 Vacuum Pipe Assembly - Cut and thread pipe in to workable size
10M50083M | Completion | BUP | 10.2 Fit and properly join the pipe assembly
10M50083M | Completion | BUP | 10.3 Clean mounting block (on QSA)
10M50083M | Completion | BUP | 10.4 Fit vacuum hose with soft pliable gasket
10M50083M | Completion | BUP | 11.1 Gummies - Measure and mark holes
10M50083M | Completion | BUP | 11.2 Drill and tap holes
10M50083M | Completion | BUP | 11.3 Load gummies and semi-tighten (check straightness)
10M50083M | Completion | BUP | 11.4 Check the alignment of gummies
10M50083M | Completion | BUP | 11.5 Tighten the bolts on gummies
10M50083M | Completion | Coach Build | 12.1 Saloon Floor Arrangement - Use glue to bond masonite packers on the corrugated floor for levelness
10M50083M | Completion | Coach Build | 12.2 Vanish/ auto-coat the bottom side of the floorboard
10M50083M | Completion | Coach Build | 12.3 Fit floorboards on top of corrugated floor and tighten using self-tapping screws
10M50083M | Completion | Coach Build | 12.4 Measure floor for levelness
10M50083M | Completion | Coach Build | 12.5 Apply body filler on all screws & floorboard joints
10M50083M | Completion | Coach Build | 13.1 Saloon Sanding Floor - Sand floor (ensure that body filler is fully cured before sanding)
10M50083M | Completion | Coach Build | 13.2 Check levelness
10M50083M | Completion | Coach Build | 13.3 Clean floorboards
10M50083M | Completion | Coach Build | 13.4 Fit side metal plate
10M50083M | Completion | Coach Build | 14.1 Marley or carpet - Apply contact adhesive evenly on both marley & floorboards
10M50083M | Completion | Coach Build | 14.2 Lay marley/carpet on the floor and weld marley joints
10M50083M | Completion | Coach Build | 14.3 Install skirting to secure Marley/Carpet
10M50083M | Completion | Coach Build | 15.1 Windows - Fit and align window to position, clamp the window and mark holes
10M50083M | Completion | Coach Build | 15.2 Drill holes for the windows & clean off the shavings
10M50083M | Completion | Coach Build | 15.3 Tighten the window using rivets
10M50083M | Completion | Coach Build | 15.4 Check for gaps and seal appropriately
10M50083M | Completion | Coach Build | 15.5 Post window assembly quality inspection
10M50083M | Completion | Electrical | 16.1 Jumper Cables No.1 and No.2 End - Re-tap all holes to be used
10M50083M | Completion | Electrical | 16.2 Insert jumper gasket
10M50083M | Completion | Electrical | 16.3 Insert complete jumper
10M50083M | Completion | Electrical | 16.4 Tighten fixings and apply sealant
10M50083M | Completion | Electrical | 16.5 Re-tap all holes to be used
10M50083M | Completion | Electrical | 17.1 Jumper Plug Connection No.1 and No.2 End - Sort out wires
10M50083M | Completion | Electrical | 17.2 Insert sleeving, I-dents & cable ties
10M50083M | Completion | Electrical | 17.3 Size, lug & terminate wires
10M50083M | Completion | Electrical | 17.4 Connect wires to body end terminal block
10M50083M | Completion | BUP | 18.1 Vacuum Brake Installation - Fit the V-hangers (4) and brake shaft (2)
10M50083M | Completion | BUP | 18.2 Pre-fit the V-hanger using bolts and split pins
10M50083M | Completion | BUP | 18.3 Fit the brake shaft (using the crane/forklift)
10M50083M | Completion | BUP | 18.4 Fit the brake shaft (using the crane/forklift)
10M50083M | Completion | BUP | 18.5 Lock V-hanger using bolts and split pins
10M50083M | Completion | BUP | 18.6 Fit the safety loops and secure by bolts and nuts
10M50083M | Completion | BUP | 18.7 Fit vacuum cylinder using mounting bracket and secure with bolt and nut
10M50083M | Completion | BUP | 18.8 Fit ball valve on the cylinder and release wire
10M50083M | Completion | BUP | 18.9 Connect vacuum cylinder rods with brake shaft lever using pin and split pins
10M50083M | Completion | BUP | 18.10 Fit slack adjuster on the brake shaft
10M50083M | Completion | BUP | 18.11 Join slack adjusters with pull rods using bolt and pin lock with split pins
10M50083M | Completion | BUP | 18.12 Fit release spring
10M50083M | Completion | BUP | 18.13 Fit the reservoirs, secure them with strip bracket
10M50083M | Completion | BUP | 18.14 Fit small reservoirs using strip bracket
10M50083M | Completion | BUP | 18.15 Fit the flexible rubber pipe
10M50083M | Completion | BUP | 18.16 Install handbrake
10M50083M | Completion | BUP | 19.1 Bogies - Crack checks done on the bogie frames
10M50083M | Completion | BUP | 19.2 Diagonal checks done on the bogie frames
10M50083M | Completion | BUP | 19.3 Fit bolster
10M50083M | Completion | BUP | 19.4 Fit equalizing beam
10M50083M | Completion | BUP | 19.5 Fit bolster and equalizing spring
10M50083M | Completion | BUP | 19.6 Fit wheels (with gear cases for Motor coaches)
10M50083M | Completion | BUP | 19.7 Fit brake rigging
10M50083M | Completion | BUP | 20.1 QSA - Clean mounting block (on QSA)
10M50083M | Completion | BUP | 20.2 Fit sealing rubber gasket and mount QSA valve and secure with bolt and nut
10M50083M | Completion | Coach Build | 21.1 Monsoons - Install monsoons
10M50083M | Completion | Coach Build | 21.2 Sealing of monsoons
10M50083M | Completion | Coach Build | 22.1 Canopies - Install canopies with mono bolts
10M50083M | Completion | Coach Build | 22.2 Seal roof gutters and seal canopies
10M50083M | Completion | Coach Build | 23.1 Body Insulation - Measure insulation to size
10M50083M | Completion | Coach Build | 23.2 Insert insulation in to interior coach panels
10M50083M | Completion | Coach Build | 24.1 Roof Ceiling Installation - Cut light spaces on the roof ceiling panels
10M50083M | Completion | Coach Build | 24.2 Fit interior roof ceiling panels
10M50083M | Completion | Coach Build | 24.3 Hold roof ceiling panel with self-tapping screws
10M50083M | Completion | Coach Build | 24.4 Insert ceiling moulding
10M50083M | Completion | Coach Build | 25.1 Body Side Panels - Fit fire retardant panels
10M50083M | Completion | Coach Build | 25.2 Ensure body side panels are clean and presentable
10M50083M | Completion | Coach Build | 26.1 Moulding Installation - Insert floor body side moulding
10M50083M | Completion | Coach Build | 26.2 Fitted saloon moulding
10M50083M | Completion | Coach Build | 27.1 Door Tread Plates - Place tread plate
10M50083M | Completion | Coach Build | 27.2 Drill and secure tread plates with self-taping screws
10M50083M | Completion | Coach Build | 27.3 Fit corner piece
10M50083M | Completion | Coach Build | 28.1 Sliding Door Mechanism Installation and Door Trimming - Re-tap door mechanism mounting pads
10M50083M | Completion | Coach Build | 28.2 Mount and secure door mechanism/gears
10M50083M | Completion | Coach Build | 28.3 Position guard rails, marks & drill holes
10M50083M | Completion | Coach Build | 29.1 Saloon Sliding Doors Installation - Mount the cable over the two idler pulleys & pull tight
10M50083M | Completion | Coach Build | 29.2 Fit doors onto running gears
10M50083M | Completion | Coach Build | 30.1 Water Test 2 - Emergency doors and window leaks, Sliding doors and window leaks, Canopy leaks, Nose cone leaks etc
10M50083M | Completion | Coach Build | 31.1 Draft Shields - Fit draft shields and align
10M50083M | Completion | Coach Build | 31.2 Mark and drill holes
10M50083M | Completion | Coach Build | 31.3 Tighten with self-taping screws
10M50083M | Completion | Coach Build | 32.1 Grab and Commode Handles - Mark and drill holes
10M50083M | Completion | Coach Build | 32.2 Fit grab; commode handles and align
10M50083M | Completion | Coach Build | 32.3 Tighten with self-taping screws
10M50083M | Completion | Coach Build | 33.1 Window Shrouds (A/B Side) - Pre-fit window shrouds, mark and drill the holes
10M50083M | Completion | Coach Build | 33.2 Fit window shrouds and tighten with self-tapping screws
10M50083M | Completion | Coach Build | 34.1 End Doors/Emergency Doors - Pre-fit emergency door; mark and drill holes
10M50083M | Completion | Coach Build | 34.2 Fit the complete emergency door and tighten with rivets
10M50083M | Completion | Coach Build | 34.3 Fit sealing rubbers and sealant around end door frame
10M50083M | Completion | Coach Build | 34.4 Fit slippery plates and corner piece
10M50083M | Completion | Coach Build | 35.1 Seats (A/B Side) Bracketry - Measure, line-up the seats frame bracketry & mark panels
10M50083M | Completion | Coach Build | 35.2 Drill holes on A/B side panels
10M50083M | Completion | Coach Build | 35.3 Fit and tighten seat frame bracketry against A/B side panels
10M50083M | Completion | Coach Build | 36.1 Seat Moulding (A/B Side) - Load seats moulding and place on top of bracketry according to drawing
10M50083M | Completion | Coach Build | 36.2 Drill holes and affix seats moulding onto seat bracketry using rivets
10M50083M | Completion | Electrical | 37.1 Sliding Doors - XT door termination
10M50083M | Completion | Electrical | 37.2 Install and connect emergency pushbutton
10M50083M | Completion | Electrical | 37.3 Trailer control box connection (external)
10M50083M | Completion | Electrical | 38.1 Saloon Final Connections - Fit and connect saloon and cab light
10M50083M | Completion | Electrical | 38.2 Trailer door control box connection (internal) optional
10M50083M | Completion | Electrical | 39.1 QSA Connection - Neatly complete all electrical connections and close covers
10M50083M | Completion | Electrical | 39.2 Protect electrical cables with spiral
10M50083M | Completion | Electrical | 40.1 Electrical Test - Clean coach & final inspection
10M50083M | Completion | Testing & Commissioning | 41 .1 Conduct Visual Inspection
10M50083M | Completion | Testing & Commissioning | 41.2 Conduct Static Testing (Functional) on 110V
10M50083M | Completion | Testing & Commissioning | 41.3 Conduct Dynamic Testing on 3kV
10M50083M | Completion | Testing & Commissioning | 41.4 Confirm no oustanding snags
10M50083M | Completion | Testing & Commissioning | 41.5 Management walk about
10M50083M | Completion | Testing & Commissioning | 41.6 Invite PRASA QC for Coach Inspection
10M50083M | Completion | Testing & Commissioning | 41.7 Attend to PRASA snags
10M50083M | Completion | Testing & Commissioning | 41.8 Invite PRASA QC for Verification
10M50083M | Completion | PRASA | 42.1 Issue Completion Certificate