## Sheet1 (3)
coach_number | section | task | hours | completed | completed_date
10M50083M | Completion | 3.1 Cut and replace old end step | 8
10M50083M | Completion | 3.2 Straighten interior floor channels | 8
10M50083M | Completion | 3.3 Remove all screws on the floor channels | 8
10M50083M | Completion | 3.4 Drill water ingress holes on body end | 8
10M50083M | Completion | 3.5 Fix damaged existing bracket on the underframe | 8
10M50083M | Completion | 3.6 Remove rust on the body using chipping hammer if rust detected is too deep, cut it and replace with new component | 8
10M50083M | Completion | 3.7 Inspect and weld all monsoons holes roof | 8
10M50083M | Completion | 3.8 Weld gutter holes | 8
10M50083M | Completion | 3.9 Weld and grind rust affected areas on the sole bar | 8
10M50083M | Completion | 3.10 Weld or replace all damaged small components | 8
10M50083M | Completion | 3.11 Modify seat frames | 8
10M50083M | Completion | 4.1 Shot blast coach sole bar | 8
10M50083M | Completion | 4.2 Clean the shot blast surface with air | 8
10M50083M | Completion | 4.3 Shot blast BUP small components | 8
10M50083M | Completion | 4.4 Shot blast Coachbuild small components | 8
10M50083M | Completion | 5.1 Clean dirt/dust inside the coach | 8
10M50083M | Completion | 5.2 Auto coat interior | 8
10M50083M | Completion | 5.3 Wash the underframe | 8
10M50083M | Completion | 5.4 Auto coat under frame | 8
10M50083M | Completion | 6.1 First water test - Check the coach is fully sealed. | 8
10M50083M | Completion | 6.2 Spray pressurized water where sealant is applied (on the panel joints) | 8
10M50083M | Completion | 6.3 Check if there is any leaks on windows | 8
10M50083M | Completion | 6.4 Check if there is any leaks on monsoons | 8
10M50083M | Completion | 7.1 1st Prime preparation - Sanding, Bodyfiller, Sanding , & Apply 1st primer coat | 8
10M50083M | Completion | 7.2 2nd Prime preparation - Sanding, Sealing (Sika Flex) & Apply final coat (different colors) | 8
10M50083M | Completion | 8.1 Inspect all electrical wiring | 8
10M50083M | Completion | 8.2 Route train line through the conduits and ensure continuity - Body Ends, Doors, Control box, Lights, PA switch, Emergency push button, QSA | 8
10M50083M | Completion | 8.3 Terminate cables, lug, insert I-dentS, prepare & connect bogie earth straps | 8
10M50083M | Completion | 9.1 Mechanical Draw gear/coupler installation - Fit draw gears on both ends | 8
10M50083M | Completion | 9.2 Fit draw-gear top guides | 8
10M50083M | Completion | 9.3 Fit carrier plate/draw-gear cover plate | 8
10M50083M | Completion | 9.4 Fit side plunger springs | 8
10M50083M | Completion | 9.5 Fit wear plate in a side plunger | 8
10M50083M | Completion | 9.6 Assemble & fit side plunger springs & spring guide | 8
10M50083M | Completion | 9.7 Fit coupler web plate and fit coupler guides | 8
10M50083M | Completion | 9.8 Fit coupler casting & secure them with right sized bolts and split pins | 8
10M50083M | Completion | 9.9 Fit coupler & secure coupler with split pins | 8
10M50083M | Completion | 9.10 Fit casting and secure | 8
10M50083M | Completion | 9.11 Fit buffer rod & split pins | 8
10M50083M | Completion | 9.12 Fit buffer beams plate | 8
10M50083M | Completion | 10.1 Vacuum Pipe Assembly - Cut and thread pipe in to workable size | 8
10M50083M | Completion | 10.2 Fit and properly join the pipe assembly | 8
10M50083M | Completion | 10.3 Clean mounting block (on QSA) | 8
10M50083M | Completion | 10.4 Fit vacuum hose with soft pliable gasket | 8
10M50083M | Completion | 11.1 Gummies - Measure and mark holes | 8
10M50083M | Completion | 11.2 Drill and tap holes | 8
10M50083M | Completion | 11.3 Load gummies and semi-tighten (check straightness) | 8
10M50083M | Completion | 11.4 Check the alignment of gummies | 8
10M50083M | Completion | 11.5 Tighten the bolts on gummies | 8
10M50083M | Completion | 12.1 Saloon Floor Arrangement - Use glue to bond masonite packers on the corrugated floor for levelness | 8
10M50083M | Completion | 12.2 Vanish/ auto-coat the bottom side of the floorboard | 8
10M50083M | Completion | 12.3 Fit floorboards on top of corrugated floor and tighten using self-tapping screws | 8
10M50083M | Completion | 12.4 Measure floor for levelness | 8
10M50083M | Completion | 12.5 Apply body filler on all screws & floorboard joints | 8
10M50083M | Completion | 13.1 Saloon Sanding Floor - Sand floor (ensure that body filler is fully cured before sanding) | 8
10M50083M | Completion | 13.2 Check levelness | 8
10M50083M | Completion | 13.3 Clean floorboards | 8
10M50083M | Completion | 13.4 Fit side metal plate | 8
10M50083M | Completion | 14.1 Marley or carpet - Apply contact adhesive evenly on both marley & floorboards | 8
10M50083M | Completion | 14.2 Lay marley/carpet on the floor and weld marley joints | 8
10M50083M | Completion | 14.3 Install skirting to secure Marley/Carpet | 8
10M50083M | Completion | 15.1 Windows - Fit and align window to position, clamp the window and mark holes | 8
10M50083M | Completion | 15.2 Drill holes for the windows & clean off the shavings | 8
10M50083M | Completion | 15.3 Tighten the window using rivets | 8
10M50083M | Completion | 15.4 Check for gaps and seal appropriately | 8
10M50083M | Completion | 15.5 Post window assembly quality inspection | 8
10M50083M | Completion | 16.1 Jumper Cables No.1 and No.2 End - Re-tap all holes to be used | 8
10M50083M | Completion | 16.2 Insert jumper gasket | 8
10M50083M | Completion | 16.3 Insert complete jumper | 8
10M50083M | Completion | 16.4 Tighten fixings and apply sealant | 8
10M50083M | Completion | 16.5 Re-tap all holes to be used | 8
10M50083M | Completion | 17.1 Jumper Plug Connection No.1 and No.2 End - Sort out wires | 8
10M50083M | Completion | 17.2 Insert sleeving, I-dents & cable ties | 8
10M50083M | Completion | 17.3 Size, lug & terminate wires | 8
10M50083M | Completion | 17.4 Connect wires to body end terminal block | 8
10M50083M | Completion | 18.1 Vacuum Brake Installation - Fit the V-hangers (4) and brake shaft (2) | 8
10M50083M | Completion | 18.2 Pre-fit the V-hanger using bolts and split pins | 8
10M50083M | Completion | 18.3 Fit the brake shaft (using the crane/forklift) | 8
10M50083M | Completion | 18.4 Fit the brake shaft (using the crane/forklift) | 8
10M50083M | Completion | 18.5 Lock V-hanger using bolts and split pins | 8
10M50083M | Completion | 18.6 Fit the safety loops and secure by bolts and nuts | 8
10M50083M | Completion | 18.7 Fit vacuum cylinder using mounting bracket and secure with bolt and nut | 8
10M50083M | Completion | 18.8 Fit ball valve on the cylinder and release wire | 8
10M50083M | Completion | 18.9 Connect vacuum cylinder rods with brake shaft lever using pin and split pins | 8
10M50083M | Completion | 18.10 Fit slack adjuster on the brake shaft | 8
10M50083M | Completion | 18.11 Join slack adjusters with pull rods using bolt and pin lock with split pins | 8
10M50083M | Completion | 18.12 Fit release spring | 8
10M50083M | Completion | 18.13 Fit the reservoirs, secure them with strip bracket | 8
10M50083M | Completion | 18.14 Fit small reservoirs using strip bracket | 8
10M50083M | Completion | 18.15 Fit the flexible rubber pipe | 8
10M50083M | Completion | 18.16 Install handbrake | 8
10M50083M | Completion | 19.1 Bogies - Crack checks done on the bogie frames | 8
10M50083M | Completion | 19.2 Diagonal checks done on the bogie frames | 8
10M50083M | Completion | 19.3 Fit bolster | 8
10M50083M | Completion | 19.4 Fit equalizing beam | 8
10M50083M | Completion | 19.5 Fit bolster and equalizing spring | 8
10M50083M | Completion | 19.6 Fit wheels (with gear cases for Motor coaches) | 8
10M50083M | Completion | 19.7 Fit brake rigging | 8
10M50083M | Completion | 20.1 QSA - Clean mounting block (on QSA) | 8
10M50083M | Completion | 20.2 Fit sealing rubber gasket and mount QSA valve and secure with bolt and nut | 8
10M50083M | Completion | 21.1 Monsoons - Install monsoons | 8
10M50083M | Completion | 21.2 Sealing of monsoons | 8
10M50083M | Completion | 22.1 Canopies - Install canopies with mono bolts | 8
10M50083M | Completion | 22.2 Seal roof gutters and seal canopies | 8
10M50083M | Completion | 23.1 Body Insulation - Measure insulation to size | 8
10M50083M | Completion | 23.2 Insert insulation in to interior coach panels | 8
10M50083M | Completion | 24.1 Roof Ceiling Installation - Cut light spaces on the roof ceiling panels | 8
10M50083M | Completion | 24.2 Fit interior roof ceiling panels | 8
10M50083M | Completion | 24.3 Hold roof ceiling panel with self-tapping screws | 8
10M50083M | Completion | 24.4 Insert ceiling moulding | 8
10M50083M | Completion | 25.1 Body Side Panels - Fit fire retardant panels | 8
10M50083M | Completion | 25.2 Ensure body side panels are clean and presentable | 8
10M50083M | Completion | 26.1 Moulding Installation - Insert floor body side moulding | 8
10M50083M | Completion | 26.2 Fitted saloon moulding | 8
10M50083M | Completion | 27.1 Door Tread Plates - Place tread plate | 8
10M50083M | Completion | 27.2 Drill and secure tread plates with self-taping screws | 8
10M50083M | Completion | 27.3 Fit corner piece | 8
10M50083M | Completion | 28.1 Sliding Door Mechanism Installation and Door Trimming - Re-tap door mechanism mounting pads | 8
10M50083M | Completion | 28.2 Mount and secure door mechanism/gears | 8
10M50083M | Completion | 28.3 Position guard rails, marks & drill holes | 8
10M50083M | Completion | 29.1 Saloon Sliding Doors Installation - Mount the cable over the two idler pulleys & pull tight | 8
10M50083M | Completion | 29.2 Fit doors onto running gears | 8
10M50083M | Completion | 30.1 Water Test 2 - Emergency doors and window leaks, Sliding doors and window leaks, Canopy leaks, Nose cone leaks etc | 8
10M50083M | Completion | 31.1 Draft Shields - Fit draft shields and align | 8
10M50083M | Completion | 31.2 Mark and drill holes | 8
10M50083M | Completion | 31.3 Tighten with self-taping screws | 8
10M50083M | Completion | 32.1 Grab and Commode Handles - Mark and drill holes | 8
10M50083M | Completion | 32.2 Fit grab; commode handles and align | 8
10M50083M | Completion | 32.3 Tighten with self-taping screws | 8
10M50083M | Completion | 33.1 Window Shrouds (A/B Side) - Pre-fit window shrouds, mark and drill the holes | 8
10M50083M | Completion | 33.2 Fit window shrouds and tighten with self-tapping screws | 8
10M50083M | Completion | 34.1 End Doors/Emergency Doors - Pre-fit emergency door; mark and drill holes | 8
10M50083M | Completion | 34.2 Fit the complete emergency door and tighten with rivets | 8
10M50083M | Completion | 34.3 Fit sealing rubbers and sealant around end door frame | 8
10M50083M | Completion | 34.4 Fit slippery plates and corner piece | 8
10M50083M | Completion | 35.1 Seats (A/B Side) Bracketry - Measure, line-up the seats frame bracketry & mark panels | 8
10M50083M | Completion | 35.2 Drill holes on A/B side panels | 8
10M50083M | Completion | 35.3 Fit and tighten seat frame bracketry against A/B side panels | 8
10M50083M | Completion | 36.1 Seat Moulding (A/B Side) - Load seats moulding and place on top of bracketry according to drawing | 8
10M50083M | Completion | 36.2 Drill holes and affix seats moulding onto seat bracketry using rivets | 8
10M50083M | Completion | 37.1 Sliding Doors - XT door termination | 8
10M50083M | Completion | 37.2 Install and connect emergency pushbutton | 8
10M50083M | Completion | 37.3 Trailer control box connection (external) | 8
10M50083M | Completion | 38.1 Saloon Final Connections - Fit and connect saloon and cab light | 8
10M50083M | Completion | 38.2 Trailer door control box connection (internal) optional | 8
10M50083M | Completion | 39.1 QSA Connection - Neatly complete all electrical connections and close covers | 8
10M50083M | Completion | 39.2 Protect electrical cables with spiral | 8
10M50083M | Completion | 40.1 Electrical Test - Clean coach & final inspection | 8
10M50083M | Completion | 41 .1 Conduct Visual Inspection | 8
10M50083M | Completion | 41.2 Conduct Static Testing (Functional) on 110V | 8
10M50083M | Completion | 41.3 Conduct Dynamic Testing on 3kV | 8
10M50083M | Completion | 41.4 Confirm no oustanding snags | 8
10M50083M | Completion | 41.5 Management walk about | 8
10M50083M | Completion | 41.6 Invite PRASA QC for Coach Inspection | 8
10M50083M | Completion | 41.7 Attend to PRASA snags | 8
10M50083M | Completion | 41.8 Invite PRASA QC for Verification | 8
10M50083M | Completion | 42.1 Issue Completion Certificate | 8

## Sheet1 (2)
coach_number | section | task | hours | completed | completed_date
| Stripping | 2.1 Remove all interior components
| Stripping | 2.2 Remove all Exterior panels
| Stripping | 2.3 Remove all interior components
| Stripping | 2.4 Remove all exterior components
| Stripping | 2.5 Remove and strip all bogies components
| Stripping | 2.6 Remove all underframe components
| Stripping | 2.7 Remove all vestibule section components
| Completion | 3.1 Cut and replace old end step
| Completion | 3.2 Straighten interior floor channels
| Completion | 3.3 Remove all screws on the floor channels
| Completion | 3.4 Drill water ingress holes on body end
| Completion | 3.5 Fix damaged existing bracket on the underframe
| Completion | 3.6 Remove rust on the body using chipping hammer if rust detected is too deep, cut it and replace with new component
| Completion | 3.7 Inspect and weld all monsoons holes roof
| Completion | 3.8 Weld gutter holes
| Completion | 3.9 Weld and grind rust affected areas on the sole bar
| Completion | 3.10 Weld or replace all damaged small components
| Completion | 3.11 Modify seat frames
| Completion | 4.1 Shot blast coach sole bar
| Completion | 4.2 Clean the shot blast surface with air
| Completion | 4.3 Shot blast BUP small components
| Completion | 4.4 Shot blast Coachbuild small components
| Completion | 5.1 Clean dirt/dust inside the coach
| Completion | 5.2 Auto coat interior
| Completion | 5.3 Wash the underframe
| Completion | 5.4 Auto coat under frame
| Completion | 6.1 First water test - Check the coach is fully sealed.
| Completion | 6.2 Spray pressurized water where sealant is applied (on the panel joints)
| Completion | 6.3 Check if there is any leaks on windows
| Completion | 6.4 Check if there is any leaks on monsoons
| Completion | 7.1 1st Prime preparation - Sanding, Bodyfiller, Sanding , & Apply 1st primer coat
| Completion | 7.2 2nd Prime preparation - Sanding, Sealing (Sika Flex) & Apply final coat (different colors)
| Completion | 8.1 Inspect all electrical wiring
| Completion | 8.2 Route train line through the conduits and ensure continuity - Body Ends, Doors, Control box, Lights, PA switch, Emergency push button, QSA
| Completion | 8.3 Terminate cables, lug, insert I-dentS, prepare & connect bogie earth straps
| Completion | 9.1 Mechanical Draw gear/coupler installation - Fit draw gears on both ends
| Completion | 9.2 Fit draw-gear top guides
| Completion | 9.3 Fit carrier plate/draw-gear cover plate
| Completion | 9.4 Fit side plunger springs
| Completion | 9.5 Fit wear plate in a side plunger
| Completion | 9.6 Assemble & fit side plunger springs & spring guide
| Completion | 9.7 Fit coupler web plate and fit coupler guides
| Completion | 9.8 Fit coupler casting & secure them with right sized bolts and split pins
| Completion | 9.9 Fit coupler & secure coupler with split pins
| Completion | 9.10 Fit casting and secure
| Completion | 9.11 Fit buffer rod & split pins
| Completion | 9.12 Fit buffer beams plate
| Completion | 10.1 Vacuum Pipe Assembly - Cut and thread pipe in to workable size
| Completion | 10.2 Fit and properly join the pipe assembly
| Completion | 10.3 Clean mounting block (on QSA)
| Completion | 10.4 Fit vacuum hose with soft pliable gasket
| Completion | 11.1 Gummies - Measure and mark holes
| Completion | 11.2 Drill and tap holes
| Completion | 11.3 Load gummies and semi-tighten (check straightness)
| Completion | 11.4 Check the alignment of gummies
| Completion | 11.5 Tighten the bolts on gummies
| Completion | 12.1 Saloon Floor Arrangement - Use glue to bond masonite packers on the corrugated floor for levelness
| Completion | 12.2 Vanish/ auto-coat the bottom side of the floorboard
| Completion | 12.3 Fit floorboards on top of corrugated floor and tighten using self-tapping screws
| Completion | 12.4 Measure floor for levelness
| Completion | 12.5 Apply body filler on all screws & floorboard joints
| Completion | 13.1 Saloon Sanding Floor - Sand floor (ensure that body filler is fully cured before sanding)
| Completion | 13.2 Check levelness
| Completion | 13.3 Clean floorboards
| Completion | 13.4 Fit side metal plate
| Completion | 14.1 Marley or carpet - Apply contact adhesive evenly on both marley & floorboards
| Completion | 14.2 Lay marley/carpet on the floor and weld marley joints
| Completion | 14.3 Install skirting to secure Marley/Carpet
| Completion | 15.1 Windows - Fit and align window to position, clamp the window and mark holes
| Completion | 15.2 Drill holes for the windows & clean off the shavings
| Completion | 15.3 Tighten the window using rivets
| Completion | 15.4 Check for gaps and seal appropriately
| Completion | 15.5 Post window assembly quality inspection
| Completion | 16.1 Jumper Cables No.1 and No.2 End - Re-tap all holes to be used
| Completion | 16.2 Insert jumper gasket
| Completion | 16.3 Insert complete jumper
| Completion | 16.4 Tighten fixings and apply sealant
| Completion | 16.5 Re-tap all holes to be used
| Completion | 17.1 Jumper Plug Connection No.1 and No.2 End - Sort out wires
| Completion | 17.2 Insert sleeving, I-dents & cable ties
| Completion | 17.3 Size, lug & terminate wires
| Completion | 17.4 Connect wires to body end terminal block
| Completion | 18.1 Vacuum Brake Installation - Fit the V-hangers (4) and brake shaft (2)
| Completion | 18.2 Pre-fit the V-hanger using bolts and split pins
| Completion | 18.3 Fit the brake shaft (using the crane/forklift)
| Completion | 18.4 Fit the brake shaft (using the crane/forklift)
| Completion | 18.5 Lock V-hanger using bolts and split pins
| Completion | 18.6 Fit the safety loops and secure by bolts and nuts
| Completion | 18.7 Fit vacuum cylinder using mounting bracket and secure with bolt and nut
| Completion | 18.8 Fit ball valve on the cylinder and release wire
| Completion | 18.9 Connect vacuum cylinder rods with brake shaft lever using pin and split pins
| Completion | 18.10 Fit slack adjuster on the brake shaft
| Completion | 18.11 Join slack adjusters with pull rods using bolt and pin lock with split pins
| Completion | 18.12 Fit release spring
| Completion | 18.13 Fit the reservoirs, secure them with strip bracket
| Completion | 18.14 Fit small reservoirs using strip bracket
| Completion | 18.15 Fit the flexible rubber pipe
| Completion | 18.16 Install handbrake
| Completion | 19.1 Bogies - Crack checks done on the bogie frames
| Completion | 19.2 Diagonal checks done on the bogie frames
| Completion | 19.3 Fit bolster
| Completion | 19.4 Fit equalizing beam
| Completion | 19.5 Fit bolster and equalizing spring
| Completion | 19.6 Fit wheels (with gear cases for Motor coaches)
| Completion | 19.7 Fit brake rigging
| Completion | 20.1 QSA - Clean mounting block (on QSA)
| Completion | 20.2 Fit sealing rubber gasket and mount QSA valve and secure with bolt and nut
| Completion | 21.1 Monsoons - Install monsoons
| Completion | 21.2 Sealing of monsoons
| Completion | 22.1 Canopies - Install canopies with mono bolts
| Completion | 22.2 Seal roof gutters and seal canopies
| Completion | 23.1 Body Insulation - Measure insulation to size
| Completion | 23.2 Insert insulation in to interior coach panels
| Completion | 24.1 Roof Ceiling Installation - Cut light spaces on the roof ceiling panels
| Completion | 24.2 Fit interior roof ceiling panels
| Completion | 24.3 Hold roof ceiling panel with self-tapping screws
| Completion | 24.4 Insert ceiling moulding
| Completion | 25.1 Body Side Panels - Fit fire retardant panels
| Completion | 25.2 Ensure body side panels are clean and presentable
| Completion | 26.1 Moulding Installation - Insert floor body side moulding
| Completion | 26.2 Fitted saloon moulding
| Completion | 27.1 Door Tread Plates - Place tread plate
| Completion | 27.2 Drill and secure tread plates with self-taping screws
| Completion | 27.3 Fit corner piece
| Completion | 28.1 Sliding Door Mechanism Installation and Door Trimming - Re-tap door mechanism mounting pads
| Completion | 28.2 Mount and secure door mechanism/gears
| Completion | 28.3 Position guard rails, marks & drill holes
| Completion | 29.1 Saloon Sliding Doors Installation - Mount the cable over the two idler pulleys & pull tight
| Completion | 29.2 Fit doors onto running gears
| Completion | 30.1 Water Test 2 - Emergency doors and window leaks, Sliding doors and window leaks, Canopy leaks, Nose cone leaks etc
| Completion | 31.1 Draft Shields - Fit draft shields and align
| Completion | 31.2 Mark and drill holes
| Completion | 31.3 Tighten with self-taping screws
| Completion | 32.1 Grab and Commode Handles - Mark and drill holes
| Completion | 32.2 Fit grab; commode handles and align
| Completion | 32.3 Tighten with self-taping screws
| Completion | 33.1 Window Shrouds (A/B Side) - Pre-fit window shrouds, mark and drill the holes
| Completion | 33.2 Fit window shrouds and tighten with self-tapping screws
| Completion | 34.1 End Doors/Emergency Doors - Pre-fit emergency door; mark and drill holes
| Completion | 34.2 Fit the complete emergency door and tighten with rivets
| Completion | 34.3 Fit sealing rubbers and sealant around end door frame
| Completion | 34.4 Fit slippery plates and corner piece
| Completion | 35.1 Seats (A/B Side) Bracketry - Measure, line-up the seats frame bracketry & mark panels
| Completion | 35.2 Drill holes on A/B side panels
| Completion | 35.3 Fit and tighten seat frame bracketry against A/B side panels
| Completion | 36.1 Seat Moulding (A/B Side) - Load seats moulding and place on top of bracketry according to drawing
| Completion | 36.2 Drill holes and affix seats moulding onto seat bracketry using rivets
| Completion | 37.1 Sliding Doors - XT door termination
| Completion | 37.2 Install and connect emergency pushbutton
| Completion | 37.3 Trailer control box connection (external)
| Completion | 38.1 Saloon Final Connections - Fit and connect saloon and cab light
| Completion | 38.2 Trailer door control box connection (internal) optional
| Completion | 39.1 QSA Connection - Neatly complete all electrical connections and close covers
| Completion | 39.2 Protect electrical cables with spiral
| Completion | 40.1 Electrical Test - Clean coach & final inspection
| Completion | 41 .1 Conduct Visual Inspection
| Completion | 41.2 Conduct Static Testing (Functional) on 110V
| Completion | 41.3 Conduct Dynamic Testing on 3kV
| Completion | 41.4 Confirm no oustanding snags
| Completion | 41.5 Management walk about
| Completion | 41.6 Invite PRASA QC for Coach Inspection
| Completion | 41.7 Attend to PRASA snags
| Completion | 41.8 Invite PRASA QC for Verification
| Completion | 42.1 Issue Completion Certificate

## Sheet1
coach_number | section | task | hours | completed | completed_date
| Coach Build | 2.1 Remove all interior components
| Coach Build | 2.2 Remove all Exterior panels
| Electrical | 2.3 Remove all interior components
| Electrical | 2.4 Remove all exterior components
| Electrical | 2.5 Remove and strip all bogies components
| Electrical | 2.6 Remove all underframe components
| Electrical | 2.7 Remove all vestibule section components
| Structural | 3.1 Cut and replace old end step
| Structural | 3.2 Straighten interior floor channels
| Structural | 3.3 Remove all screws on the floor channels
| Structural | 3.4 Drill water ingress holes on body end
| Structural | 3.5 Fix damaged existing bracket on the underframe
| Structural | 3.6 Remove rust on the body using chipping hammer if rust detected is too deep, cut it and replace with new component
| Structural | 3.7 Inspect and weld all monsoons holes roof
| Structural | 3.8 Weld gutter holes
| Structural | 3.9 Weld and grind rust affected areas on the sole bar
| Structural | 3.10 Weld or replace all damaged small components
| Structural | 3.11 Modify seat frames
| Paint Works | 4.1 Shot blast coach sole bar
| Paint Works | 4.2 Clean the shot blast surface with air
| Paint Works | 4.3 Shot blast BUP small components
| Paint Works | 4.4 Shot blast Coachbuild small components
| Paint Works | 5.1 Clean dirt/dust inside the coach
| Paint Works | 5.2 Auto coat interior
| Paint Works | 5.3 Wash the underframe
| Paint Works | 5.4 Auto coat under frame
| Coach Build | 6.1 First water test - Check the coach is fully sealed.
| Coach Build | 6.2 Spray pressurized water where sealant is applied (on the panel joints)
| Coach Build | 6.3 Check if there is any leaks on windows
| Coach Build | 6.4 Check if there is any leaks on monsoons
| Paint Works | 7.1 1st Prime preparation - Sanding, Bodyfiller, Sanding , & Apply 1st primer coat
| Paint Works | 7.2 2nd Prime preparation - Sanding, Sealing (Sika Flex) & Apply final coat (different colors)
| Electrical | 8.1 Inspect all electrical wiring
| Electrical | 8.2 Route train line through the conduits and ensure continuity - Body Ends, Doors, Control box, Lights, PA switch, Emergency push button, QSA
| Electrical | 8.3 Terminate cables, lug, insert I-dentS, prepare & connect bogie earth straps
| BUP | 9.1 Mechanical Draw gear/coupler installation - Fit draw gears on both ends
| BUP | 9.2 Fit draw-gear top guides
| BUP | 9.3 Fit carrier plate/draw-gear cover plate
| BUP | 9.4 Fit side plunger springs
| BUP | 9.5 Fit wear plate in a side plunger
| BUP | 9.6 Assemble & fit side plunger springs & spring guide
| BUP | 9.7 Fit coupler web plate and fit coupler guides
| BUP | 9.8 Fit coupler casting & secure them with right sized bolts and split pins
| BUP | 9.9 Fit coupler & secure coupler with split pins
| BUP | 9.10 Fit casting and secure
| BUP | 9.11 Fit buffer rod & split pins
| BUP | 9.12 Fit buffer beams plate
| BUP | 10.1 Vacuum Pipe Assembly - Cut and thread pipe in to workable size
| BUP | 10.2 Fit and properly join the pipe assembly
| BUP | 10.3 Clean mounting block (on QSA)
| BUP | 10.4 Fit vacuum hose with soft pliable gasket
| BUP | 11.1 Gummies - Measure and mark holes
| BUP | 11.2 Drill and tap holes
| BUP | 11.3 Load gummies and semi-tighten (check straightness)
| BUP | 11.4 Check the alignment of gummies
| BUP | 11.5 Tighten the bolts on gummies
| Coach Build | 12.1 Saloon Floor Arrangement - Use glue to bond masonite packers on the corrugated floor for levelness
| Coach Build | 12.2 Vanish/ auto-coat the bottom side of the floorboard
| Coach Build | 12.3 Fit floorboards on top of corrugated floor and tighten using self-tapping screws
| Coach Build | 12.4 Measure floor for levelness
| Coach Build | 12.5 Apply body filler on all screws & floorboard joints
| Coach Build | 13.1 Saloon Sanding Floor - Sand floor (ensure that body filler is fully cured before sanding)
| Coach Build | 13.2 Check levelness
| Coach Build | 13.3 Clean floorboards
| Coach Build | 13.4 Fit side metal plate
| Coach Build | 14.1 Marley or carpet - Apply contact adhesive evenly on both marley & floorboards
| Coach Build | 14.2 Lay marley/carpet on the floor and weld marley joints
| Coach Build | 14.3 Install skirting to secure Marley/Carpet
| Coach Build | 15.1 Windows - Fit and align window to position, clamp the window and mark holes
| Coach Build | 15.2 Drill holes for the windows & clean off the shavings
| Coach Build | 15.3 Tighten the window using rivets
| Coach Build | 15.4 Check for gaps and seal appropriately
| Coach Build | 15.5 Post window assembly quality inspection
| Electrical | 16.1 Jumper Cables No.1 and No.2 End - Re-tap all holes to be used
| Electrical | 16.2 Insert jumper gasket
| Electrical | 16.3 Insert complete jumper
| Electrical | 16.4 Tighten fixings and apply sealant
| Electrical | 16.5 Re-tap all holes to be used
| Electrical | 17.1 Jumper Plug Connection No.1 and No.2 End - Sort out wires
| Electrical | 17.2 Insert sleeving, I-dents & cable ties
| Electrical | 17.3 Size, lug & terminate wires
| Electrical | 17.4 Connect wires to body end terminal block
| BUP | 18.1 Vacuum Brake Installation - Fit the V-hangers (4) and brake shaft (2)
| BUP | 18.2 Pre-fit the V-hanger using bolts and split pins
| BUP | 18.3 Fit the brake shaft (using the crane/forklift)
| BUP | 18.4 Fit the brake shaft (using the crane/forklift)
| BUP | 18.5 Lock V-hanger using bolts and split pins
| BUP | 18.6 Fit the safety loops and secure by bolts and nuts
| BUP | 18.7 Fit vacuum cylinder using mounting bracket and secure with bolt and nut
| BUP | 18.8 Fit ball valve on the cylinder and release wire
| BUP | 18.9 Connect vacuum cylinder rods with brake shaft lever using pin and split pins
| BUP | 18.10 Fit slack adjuster on the brake shaft
| BUP | 18.11 Join slack adjusters with pull rods using bolt and pin lock with split pins
| BUP | 18.12 Fit release spring
| BUP | 18.13 Fit the reservoirs, secure them with strip bracket
| BUP | 18.14 Fit small reservoirs using strip bracket
| BUP | 18.15 Fit the flexible rubber pipe
| BUP | 18.16 Install handbrake
| BUP | 19.1 Bogies - Crack checks done on the bogie frames
| BUP | 19.2 Diagonal checks done on the bogie frames
| BUP | 19.3 Fit bolster
| BUP | 19.4 Fit equalizing beam
| BUP | 19.5 Fit bolster and equalizing spring
| BUP | 19.6 Fit wheels (with gear cases for Motor coaches)
| BUP | 19.7 Fit brake rigging
| BUP | 20.1 QSA - Clean mounting block (on QSA)
| BUP | 20.2 Fit sealing rubber gasket and mount QSA valve and secure with bolt and nut
| Coach Build | 21.1 Monsoons - Install monsoons
| Coach Build | 21.2 Sealing of monsoons
| Coach Build | 22.1 Canopies - Install canopies with mono bolts
| Coach Build | 22.2 Seal roof gutters and seal canopies
| Coach Build | 23.1 Body Insulation - Measure insulation to size
| Coach Build | 23.2 Insert insulation in to interior coach panels
| Coach Build | 24.1 Roof Ceiling Installation - Cut light spaces on the roof ceiling panels
| Coach Build | 24.2 Fit interior roof ceiling panels
| Coach Build | 24.3 Hold roof ceiling panel with self-tapping screws
| Coach Build | 24.4 Insert ceiling moulding
| Coach Build | 25.1 Body Side Panels - Fit fire retardant panels
| Coach Build | 25.2 Ensure body side panels are clean and presentable
| Coach Build | 26.1 Moulding Installation - Insert floor body side moulding
| Coach Build | 26.2 Fitted saloon moulding
| Coach Build | 27.1 Door Tread Plates - Place tread plate
| Coach Build | 27.2 Drill and secure tread plates with self-taping screws
| Coach Build | 27.3 Fit corner piece
| Coach Build | 28.1 Sliding Door Mechanism Installation and Door Trimming - Re-tap door mechanism mounting pads
| Coach Build | 28.2 Mount and secure door mechanism/gears
| Coach Build | 28.3 Position guard rails, marks & drill holes
| Coach Build | 29.1 Saloon Sliding Doors Installation - Mount the cable over the two idler pulleys & pull tight
| Coach Build | 29.2 Fit doors onto running gears
| Coach Build | 30.1 Water Test 2 - Emergency doors and window leaks, Sliding doors and window leaks, Canopy leaks, Nose cone leaks etc
| Coach Build | 31.1 Draft Shields - Fit draft shields and align
| Coach Build | 31.2 Mark and drill holes
| Coach Build | 31.3 Tighten with self-taping screws
| Coach Build | 32.1 Grab and Commode Handles - Mark and drill holes
| Coach Build | 32.2 Fit grab; commode handles and align
| Coach Build | 32.3 Tighten with self-taping screws
| Coach Build | 33.1 Window Shrouds (A/B Side) - Pre-fit window shrouds, mark and drill the holes
| Coach Build | 33.2 Fit window shrouds and tighten with self-tapping screws
| Coach Build | 34.1 End Doors/Emergency Doors - Pre-fit emergency door; mark and drill holes
| Coach Build | 34.2 Fit the complete emergency door and tighten with rivets
| Coach Build | 34.3 Fit sealing rubbers and sealant around end door frame
| Coach Build | 34.4 Fit slippery plates and corner piece
| Coach Build | 35.1 Seats (A/B Side) Bracketry - Measure, line-up the seats frame bracketry & mark panels
| Coach Build | 35.2 Drill holes on A/B side panels
| Coach Build | 35.3 Fit and tighten seat frame bracketry against A/B side panels
| Coach Build | 36.1 Seat Moulding (A/B Side) - Load seats moulding and place on top of bracketry according to drawing
| Coach Build | 36.2 Drill holes and affix seats moulding onto seat bracketry using rivets
| Electrical | 37.1 Sliding Doors - XT door termination
| Electrical | 37.2 Install and connect emergency pushbutton
| Electrical | 37.3 Trailer control box connection (external)
| Electrical | 38.1 Saloon Final Connections - Fit and connect saloon and cab light
| Electrical | 38.2 Trailer door control box connection (internal) optional
| Electrical | 39.1 QSA Connection - Neatly complete all electrical connections and close covers
| Electrical | 39.2 Protect electrical cables with spiral
| Electrical | 40.1 Electrical Test - Clean coach & final inspection
| Testing & Commissioning | 41 .1 Conduct Visual Inspection
| Testing & Commissioning | 41.2 Conduct Static Testing (Functional) on 110V
| Testing & Commissioning | 41.3 Conduct Dynamic Testing on 3kV
| Testing & Commissioning | 41.4 Confirm no oustanding snags
| Testing & Commissioning | 41.5 Management walk about
| Testing & Commissioning | 41.6 Invite PRASA QC for Coach Inspection
| Testing & Commissioning | 41.7 Attend to PRASA snags
| Testing & Commissioning | 41.8 Invite PRASA QC for Verification
| PRASA | 42.1 Issue Completion Certificate